## Plan Veprimi
Annex1: Action Plan
I Irrigation
| Explanation |  | P | Planning |  | M&E | Monitoring & Evaluation |  |  |  | D Drainage
|  |  | F | Financing |  | A | Approval |  |  |  | DR Dams Regulations
|  |  | I | Implementation | [6 empty] | FP Flood Protection | [18 empty] | Projection for realization of the strategy objectives by 2031
[20 empty] | Projection according to current PBA 2019 -2021 ceilings | [7 empty] | Need for financing 2022-2031
| Actions | Responsibilities | [8 empty] | Implementation |  |  | Main measurable results |  |  |  | Costs | Costs | 2019 |  | 2020 |  | 2021 |  | Total 2019-2021 |  | Objective 2022-2031 |  | 2022 |  | 2023 |  | 2024 |  | 2025 |  | 2026 |  | 2027 |  | 2028 |  | 2029 |  | 2030 |  | 2031 |  | Total 2022-2031
|  | COM | MARD | RS/MARD | Consultants | RS depending by MARD | I&D Unit | WUO | MoF | Donors | Start | Duration | Expected results | Unit | Base Year 2018 | Strategic Objective | Objective 2019-2031 | Estimated Cost in USD 2019-2031 | ALL 2019-2031 | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL | Product | Costs ALL
1+2 | Total program ceiling 04240 (1+2) | [17 empty] | 88739591000 |  | 3245800000 |  | 3195800000 |  | 3205800000 |  | 9647400000 |  | 79092191000 |  | 8488252124 |  | 8552252124 |  | 8338401552 |  | 7876909552 |  | 7940909548 |  | 8419472175 |  | 9233762175 |  | 8886193175 |  | 6049437131 |  | 1677614200 |  | 79092191000
1 | Strategic Objectives | [16 empty] | 717278100 | 78900591000 |  | 2747800000 |  | 2688800000 |  | 2695800000 |  | 8132400000 |  | 70768191000 |  | 7873252124 |  | 7873252124 |  | 7595401552 |  | 7069909552 |  | 7069909548 |  | 7484472175 |  | 8234762175 |  | 7823193175 |  | 4898437131 |  | 1216614200 |  | 70768191000
| Irrigation | [16 empty] | 253620100 | 27898211000 | 15000 | 1640000000 | 15000 | 1540000000 | 15000 | 1540000000 | 45000 | 4720000000 | 85000 | 23178211000 | 10000 | 2726840000 | 10000 | 2726840000 | 10000 | 2726840000 | 10000 | 2726840000 | 10000 | 2726840000 | 10000 | 2726840000 | 12500 | 3408550000 | 12500 | 3408621000 | 0 | 0 |  |  | 85000 | 23178211000
| Rehabilitation and modernization of irrigation infrastructure to enable irrigation on equipped irrigation area | [12 empty] | ha | 230000 | 360000 | 130000 | 253620100 | 27898211000 | 15000 | 1640000000 | 15000 | 1540000000 | 15000 | 1540000000 | 45000 | 4720000000 | 85000 | 23178211000 | 10000 | 2726840000 | 10000 | 2726840000 | 10000 | 2726840000 | 10000 | 2726840000 | 10000 | 2726840000 | 10000 | 2726840000 | 12500 | 3408550000 | 12500 | 3408621000 |  |  |  |  | 85000 | 23178211000
| Drainage | [16 empty] | 56532000 | 6218520000 |  | 192000000 |  | 233000000 |  | 240000000 |  | 665000000 |  | 5553520000 |  | 1336671144 |  | 1336671144 |  | 1058820572 |  | 533328572 |  | 533328568 |  | 343060000 |  | 411640000 |  | 0 | [5 empty] | 5553520000
| Restoration of drainage infrastructure to optimal parameters on potentially drainable surface | [12 empty] | ha | 270000 | 280000 | 10000 | 15924000 | 1751640000 |  | 0 |  | 0 |  | 0 | 0 |  | 10000 | 1751640000 | 3500 | 613074000 | 3500 | 613074000 | 3000 | 525492000 | [14 empty] | 10000 | 1751640000
| Drainage network cleaning | [12 empty] | m3 | 2000000 | 22000000 | 20000000 | 28500000 | 3135000000 | 1600000 | 192000000 | 2000000 | 233000000 | 2000000 | 240000000 | 5600000 | 665000000 | 14400000 | 2470000000 | 2000000 | 343060000 | 2000000 | 343060000 | 2000000 | 343060000 | 2000000 | 343060000 | 2000000 | 343060000 | 2000000 | 343060000 | 2400000 | 411640000 | [6 empty] | 14400000 | 2470000000
| Drainage area with main drainage network cleaned as annual cyclic process | [18 empty] | 45000 |  | 45000 |  | 45000 |  | 135000 | 0 | 270000 |  | 45000 |  | 45000 |  | 45000 |  | 45000 |  | 45000 |  | 45000 |  | 45000 | [7 empty] | 315000 | 0
| Rehabilitation of 14 hydrovoires | [12 empty] | hydrovoires | 0 | 14 | 14 | 12108000 | 1331880000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1331880000 | 4 | 380537144 | 4 | 380537144 | 2 | 190268572 | 2 | 190268572 | 2 | 190268568 | [10 empty] | 14 | 1331880000
| Dam Safety | [16 empty] | 130276000 | 14330360000 | 5 | 200000000 | 5 | 200000000 | 5 | 200000000 | 15 | 600000000 | 395 | 13730360000 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 35 | 1216614200 | 395 | 13730360000
| Rehabilitimi of about 410 dams (or about 65% of total number) to increase their safety and to guarantee the water resources for existing irrigation schemes | [12 empty] | dams | 0 | 410 | 410 | 130276000 | 14330360000 | 5 | 200000000 | 5 | 200000000 | 5 | 200000000 | 15 | 600000000 | 395 | 13730360000 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 40 | 1390416200 | 35 | 1216614200 | 395 | 13730360000
| Flood Protection | [16 empty] | 276850000 | 30453500000 | 12 | 715800000 | 12 | 715800000 | 12 | 715800000 | 36 | 2147400000 | 234 | 28306100000 | 20 | 2419324780 | 20 | 2419324780 | 20 | 2419324780 | 20 | 2419324780 | 20 | 2419324780 | 25 | 3024155975 | 25 | 3024155975 | 25 | 3024155975 | 29 | 3508020931 |  |  | 234 | 28306100000
| Increasing the safety of protection against river and marine floods, through the rehabilitation / reconstruction of existing embankments and the construction of new structures | [12 empty] | km embakments | 30 | 300 | 270 | 276850000 | 30453500000 | 12 | 715800000 | 12 | 715800000 | 12 | 715800000 | 36 | 2147400000 | 234 | 28306100000 | 20 | 2419324780 | 20 | 2419324780 | 20 | 2419324780 | 20 | 2419324780 | 20 | 2419324780 | 25 | 3024155975 | 25 | 3024155975 | 25 | 3024155975 | 29 | 3508020931 | 30 | 3628987244 | 234 | 28306100000
[14 empty] | ha |  | 130000
2 | Maintenance (for annual cyclic processes and after-investment maintenance) | [17 empty] | 9839000000 |  | 498000000 |  | 507000000 |  | 510000000 |  | 1515000000 |  | 8324000000 |  | 615000000 |  | 679000000 |  | 743000000 |  | 807000000 |  | 871000000 |  | 935000000 |  | 999000000 |  | 1063000000 |  | 1151000000 |  | 461000000 |  | 8324000000
Irrigation
[13 empty] | Silt removal from drainage system (maintenance) | m3 |  |  |  |  | 0 | 200000 |  | 220000 |  | 220000 |  | 640000 | 0 | 1260000 |  | 140000 |  | 140000 |  | 140000 |  | 140000 |  | 140000 |  | 140000 |  | 140000 |  | 140000 |  | 140000 |  |  |  | 1260000 | 0
[14 empty] | km |  |  |  |  | 0 | 100 |  | 110 |  | 110 |  | 320 | 0 | 1251 |  | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 140 |  | 135 |  | 136 |  |  |  | 1251 | 0
[13 empty] | Irrigation area with maintained irrigation main system | ha |  |  |  |  | 1001000000 | 25000 | 61000000 | 25000 | 65000000 | 25000 | 65000000 | 75000 | 191000000 | 225000 | 810000000 | 25000 | 90000000 | 25000 | 90000000 | 25000 | 90000000 | 25000 | 90000000 | 25000 | 90000000 | 25000 | 90000000 | 25000 | 90000000 | 25000 | 90000000 | 25000 | 90000000 |  |  | 225000 | 810000000
[13 empty] | Expenditures for irrigation pumping stations functionality (electrical supply and maintenance about 8000 ALL/ha) | about 300 pumping station / irrigation of about 75 000 ha |  |  |  |  | 2904000000 | [6 empty] | 0 | 0 | Totali 75 000 ha me progres vjetor rreth 8000 ha / vit | 2904000000 |  | 64000000 |  | 128000000 |  | 192000000 |  | 256000000 |  | 320000000 |  | 384000000 |  | 448000000 |  | 512000000 |  | 600000000 |  |  | 0 | 2904000000
Drainage
[13 empty] | Expenditures for 27 hydrovoires functionality (electrical supply and periodic maintenance) | hydrovoires draining in 70 000 ha |  |  |  |  | 2568000000 | 70000 | 185000000 | 70000 | 190000000 | 70000 | 193000000 | 70000/vit | 568000000 | 70000/vit | 2000000000 | 70000 | 200000000 | 70000 | 200000000 | 70000 | 200000000 | 70000 | 200000000 | 70000 | 200000000 | 70000 | 200000000 | 70000 | 200000000 | 70000 | 200000000 | 70000 | 200000000 | 70000 | 200000000 |  | 2000000000
Dam Safety
[13 empty] | Inspection of dam safety | 600 dams/year |  |  |  |  | 30000000 | [6 empty] | 0 | 0 | 600 diga/vit | 30000000 | 600 | 3000000 | 600 | 3000000 | 600 | 3000000 | 600 | 3000000 | 600 | 3000000 | 600 | 3000000 | 600 | 3000000 | 600 | 3000000 | 600 | 3000000 | 600 | 3000000 | 6000 | 30000000
Flood Protection
[13 empty] | Inspection and maintenance of embakments | 500 km/year |  |  |  |  | 60000000 | [6 empty] | 0 | 0 | 500km/vit | 60000000 | 500 | 6000000 | 500 | 6000000 | 500 | 6000000 | 500 | 6000000 | 500 | 6000000 | 500 | 6000000 | 500 | 6000000 | 500 | 6000000 | 500 | 6000000 | 500 | 6000000 | 5000 | 60000000
| Infrastructure Operation | [11 empty] | O&M employers (approximately 350 employers) | 350 employers |  |  |  |  | 3276000000 | 350 | 252000000 | 350 | 252000000 | 350 | 252000000 | 350 pun/vit | 756000000 | 350 pun/vit | 2520000000 | 350 | 252000000 | 350 | 252000000 | 350 | 252000000 | 350 | 252000000 | 350 | 252000000 | 350 | 252000000 | 350 | 252000000 | 350 | 252000000 | 350 | 252000000 | 350 | 252000000 | 350/ work/year | 2520000000
| Irrigation | [16 empty] | 253620100 | 27898211000 | 15000 | 1640000000 | 15000 | 1540000000 | 15000 | 1540000000 | 45000 | 4720000000 | 85300 | 23178211000
Irrigation and Agriculture
| I-1. Irrigation projects will be arranged with parallel agricultural projects through grants | [9 empty] | Short Term | 10 years | Parallel projects in irrigation & agriculture that provides synergy
| I-2. Irrigation and agriculture projects will focus mostly on small farm productivity and agri-business | [9 empty] | Short Term | 11 years | Improvement on farm income, employment, agro-processing & agro-business
| I-3. Facilitate consolidation of farm operations to enable cooperative agri-business and marketing | [9 empty] | Short Term | 12 years | Improved operation on consolidation between land and small farmers
| I-4. Research and development of high-value agriculture, crop processing and marketing and compatibility with EU standards | [9 empty] | Mid Term | 13 years | Small farmers posses access for capital & convenient agriculture & access on business at EU markets
Development
| I-5. Prepare guide for participatory rehabilitation and modernization |  | A | P,I | I |  |  |  |  | F | Short Term | 3 months | Guide on how implement rehabilitation & participatory modernization |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
| I-6. Prepare Investment Plan for rehabilitation and modernization of irrigation systems |  | A | P,I | I |  |  |  |  | F | Short Term | 1 year | Guide on how implement participatory new construction | [15 empty] | 0
| I-7. Mobilize funding for Investment Plan |  | A | P,I | I | I |  |  |  | F | Short Term | 6 months -1 year | Investments Plans for rehabilitation, improvement & modernization |  |  |  |  | 10000 | 1100000 | [9 empty] | 1100000
| I-8. Design arrangement for farmer cost sharing of investments |  | A | P,I | [5 empty] | F | Short Term | 4 years | Sufficient funds and assistance in project for Investment Plans | [15 empty] | 0
| I-9. WUO to engage in joint investment in rehabilitation at tertiary level |  | A | P,I |  | I | I |  |  | F | Short Term | 3 months | Agreement on how the farmers have to invest on rehabilitation & modernization |  |  |  |  | 1000000 | 110000000 | [9 empty] | 110000000
| I-10. Rehabilitation of irrigation serving 100,000 ha |  | A |  |  |  | A, M&E | A,P, I, F |  |  | Short Term | 8 years | Irrigation systems are rehabilitated & WUO have the management responsibility | [15 empty] | 0
| I-11. Rehabilitation of irrigation serving 140,000 ha along with agricultural and agri-business support |  | A | P,A | I, M&E | A |  |  | F |  | Short Term | 1-2 years | Increase of irrigatable area with about 100 000 ha (started from 2015 and in continuaty) Only with WB projects are added 20 000 ha costing 24 million USD that is identified as final process) | ha | 110000 | 110000 |  | 24000000 | 2640000000 | [9 empty] | 2640000000
| I-12. Analysis and recommendations for modernization of irrigation systems |  | A | P,A | I, M&E | A | A |  | F | F | Mid Term | 10 years | Increase of irrigatable area with about 130 000 ha | ha | 0 | 130000 | 130000 | 164000000 | 18040000000 | 15000 | 1640000000 | 15000 | 1540000000 | 15000 | 1540000000 | 45000 | 4720000000 | 85000 | 13320000000
[13 empty] | free flow | ha | 0 | 55000 | 55000 | 65000000 | 7150000000 | 15000 | 1640000000 | 15000 | 1540000000 | 15000 | 1540000000 | 45000 | 4720000000 | 10000 | 2430000000
[13 empty] | partially rehabilitation | [6 empty] | 10000 | 650000000 | 10000 | 550000000 | 10000 | 550000000
[13 empty] | increase | [6 empty] | 5000 |  | 5000 |  | 5000
[13 empty] | egsisting | [6 empty] | 5000 |  | 5000 |  | 5000
[13 empty] | full rehabilitation | [6 empty] | 10000 | 990000000 | 10000 | 990000000 | 10000 | 990000000
[13 empty] | increase | [6 empty] | 10000 |  | 10000 |  | 5000
egsisting
[13 empty] | with mechanical lifting | ha | 0 | 75000 | 75000 | 99000000 | 10890000000 | [8 empty] | 75000 | 10890000000
increase
egsisting
| I-13. Develop modernization program with intensive management practices and water measurement |  | A | P | I |  |  |  |  | F | Short Term | 6 months -1 year | Recommendations Report for Modernization Strategy
| I-14. Mobilize funding and implement modernization | A | A | P | I | I | A | A | F | F | Short Term | 6 months | Master Plan for modernization with water meters devices & intesive management |  |  |  |  | 16000 | 1760000 | [9 empty] | 1760000
| I-15. Identify which irrigation pumping stations should be rehabilitated and modernized |  | P,A | P | I, M&E | I | I,A |  | F | F | Mid Term | 12 years | Modernized system & intensive management |  |  |  |  | 9600 | 1056000 | [9 empty] | 1056000
Regulation
| I-16. Approvals for irrigation investment decisions |  | A | P | I, M&E | I | I |  | F | F | Mid Term | 1 year | Recommendations Report on identifying which pumping stations need rehabilitation & modernization (about 300 pumping stations) | pumping stations | 0 | 300 | 300 | 60000000 | 6600000000 | [8 empty] | 300 | 6600000000
| I-17. Supervision of irrigation rehabilitation, modernization, development and management | [9 empty] | Short Term | Approximately 6 years | Approval and adaption of Investments Plans | bar: A to P
| I-18. Monitor irrigation investment works | [9 empty] | Short Term | Continuaty | Consistency with irrigation policies, laws, regulation and standarts | bar: P to A
| I-19. Guide for Irrigation Management Audits prepared | [9 empty] | Short Term | Continuaty | Identifying needs for capacity building & support services | bar: P to A
| I-20. Irrigation Drainage Unite / MARD guide for Irrigation Management Audits | A: A; P: P; I: I; F: F | Short Term | 1 month | Guide on how conduct Irrigation Management Audit |  |  |  |  | 6500 | 715000 | [9 empty] | 715000
| I-21. Irrigation Management Audits implemented | A: A; P: P; I: I; F: F | Mid Term | In continuaty long term | Monitored Irrigation Performance, capacity building & recommended support services |  |  |  |  | 4000 | 440000 | [9 empty] | 440000
| I-22. Irrigation Management Audite every 2 years | A: A; P: P; I: I; F: F | Short Term | Continuaty | Consistency with policies, laws, regulations & programs. Established management capacities |  |  |  |  | 500000 | 55000000 | [9 empty] | 55000000
System governance and institutions
| I-23. Central and regional level changes of MARD | A | A,I | P,I | I | I |  |  | F |  | Short Term | 3 years | RS / MARD, Capacity Building Unit, RS depending by MARD |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
| I-24. Modules preparing, establishment of WUOs, statute & regulations | A: A; P: P; I: I; F: F | Short Term | 3 years | Statute and regulation to establish and to ensure the functionality of WUOs |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
| I-25. Establishment of WUOs Plan |  | A | P,I | I |  | I | I |  | F | Short Term | 6 months | Capacity staff to establish Irrigation Unit & WUO |  |  |  |  | 6000 | 660000 | [9 empty] | 660000
| I-26. Recruit & trainiing organization of irrigation staff | A: A; P: P; I: I; I: I; F: F | Short Term | 6 months | Capacity staff to establish Irrigation Unit & WUO |  |  |  |  | 400000 | 44000000 | [9 empty] | 44000000
| I-27. Obtain signatures of at least 51% of land owners within irrigation service area to establish WUO | A: A; P: P,I; I: I; I: I; F: F | Short Term | 5 years | WUO & WUG established on all irrigation systems of municipalities
| I-28. Role of village head before WUO are established | A: A; P: P; I: I; A: I; F: F | Short Term | 5 years | Cordination of O&M at farm level before the establishment of WUG
| I-29. Prepare guide for Management Transfer Agreement | A: A; P: P,I; I: I; F: F | Short Term | 6 months | Modules for Transferr of Irrigation Management |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
| I-30. Establishment of WUO and WUG |  | A | P | I |  | I | I |  | F | Short Term | 5 years | WUO & WUG at irrigation systems of municipalities |  |  |  |  | 640000 | 70400000 | [9 empty] | 70400000
| I-31. Prepare and adopt statute for WUO |  | A | A,P | I |  | I | I |  | F | Short Term | 5 years | All WUOs have statute
| I-32. Prepare and adopt internal by-laws for WUO |  | A | A,P | I |  | I | I |  | F | Short Term | 5 years | All WUOs have regulations
| I-33. Municipalities will manage irrigation systems (secondary and small - mid systems) | A: A; P: P; A: I; F: F | Short Term | Continuaty | Administration, management & sustainable financing of irrigation systems from municipalities
| I-34. Municipalities recruit staff for Irrigation and Drainage Unit and receive training | A: A; P: A,P; I: I; A: I,A,Municipality; F: F | Short Term | 1-3 years | I & D Units established need - based & trained. All WUO have knowledge on Operation & Management
| I-35. Transfer of management of irrigation canals | A: A; P: P; A: I; F: F | Short Term | 10 years | All WUO have knowledge on Operation & Management
| I-36. WUO officers and staff receive training in irrigation management and financing |  | A | P | P,I |  | I | I |  | F | Short Term | In continuaty long term | WUO & WUG staff are well trained on irrigation management |  |  |  |  | 80000 | 8800000 | [9 empty] | 8800000
| I-37. E drejta e përdorimit e kanaleve sekondare/terciare transferuar OPU | A: A; A: A; P: A,P,I; A: I | Mid Term | 10 years | All WUO are able & agree to take the management of secondary & tertiary canals
| I-38. Ownership of small systems transferred to WUO | A: A; A: A; P: A,P,I; A: I | Mid Term | 10 years | Clear responsibility for all. Transfer of user - right increases initiatives of benefeciaries to pay the fee & to maintain the system
| I-39. Revocation of administration responsibility of sub-system by WUO if it fails to manage | A: A; P: A,I; A: I | Mid Term | In continuaty if will occur | Revoce of management in case of failure of WUO |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
| I-40. Responsible structures / MARD will build capacity of municipal Irrigation and Drainage Units/WUO | P: A,P; I: I; A: I; F: F; F: F | Short - Mid Term | 10 years | Adequate staff of Irrigation and Drainage Units and municipalities / WUOs |  |  |  |  | 2000000 | 220000000 | [9 empty] | 220000000
| I-41. Introduction of incentive and accountability measures into the sector |  | A | P,I | I | I, M&E | I | I |  | F | Mid Term | 5 years | High Performance of staff
Management
| I-42. Key irrigation performance criteria specified and included in preparation of O&M manual | A: A; P: A,P; I: I; F: F | Mid Term | 1 year | O&M Manual prepared & used for training |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
| I-43. Irrigation Service Plan guide prepared | [9 empty] | Short Term | In continuaty long term | Adequate staff of Irrigation and Drainage Units and municipalities / WUOs | bar: I to F
| I-44. Guideline of Irrigation Service Plan prepared | P: A,P; I: I; F: F | Short Term | 6 months | Irrigation Service Plan Module prepared and used in training |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
| I-45. PShU bazuar mbi kërkesat për uje | [9 empty] | Short Term | Every year | Requests on water supply & Irrigation Service Plan prepared | bar: I to A
| I-46. MBZHR synon sigurimin e fondeve për kerkime U&K | A: A,P; P: P,I; I: I; F: F | Mid Term | In continuaty long term | Program on research and inovations for irrigation & applied management
| I-47. Instalimi i mjeteve matëse të ujit | A: A; P: A,P; I: I; I: I; F: F | Mid Term | 5 years | Water measure along the main and secondary canals |  |  |  |  | 80000 | 8800000 | [9 empty] | 8800000
| I-48. Irrigation-related dispute mediation training | P: A,P; I: P,I; I: I; A: I; F: F | Mid Term | 5 years | Adequate staff of RS / MARD, I & D Units & municipalities & WUO for mediation of resolving irrigation conflicts |  |  |  |  | 4000 | 440000 | [9 empty] | 440000
Financing
| I-49. Establish principle of payment of fixed and variable costs of irrigation | A: A,I; P: I; I: I | Short Term | 2 years | A clear base established for fixed and variable irrigation fees
| I-50. Develop a Guide for Needs-based Budgeting and Irrigation Service Fees. | A: A; P: A; I: I; F: F | Short Term | 6 months | Guide on needs - based budget & payments for irrigation service & prepared and used in trainings |  |  |  |  | 4000 | 440000 | [9 empty] | 440000
| I-51. Budgets & ISP prepared | [9 empty] | Short Term | 5 years | I & D Unit of municipalities and WUO are able to prepare need-based budget and Irrigation Service Fee | bar: I to A
| I-52. Municipalities collect irrigation fixed costs | A: A,P,I; A: A,P,I | Mid Term | Continuaty | Taxes Directory in municipality will collect the fixed fee for irrigation from landowners at the equipped irrigation service area
| I-53. New procedures for fee payement and deposits | P: P; I: P,I; A: I; A: I | Short Term | Continuaty | Transparent and accountable financial management
| I-54. Policies for service offered and approved payement | A: A; P: P,I; I: I; A: I; A: I | Mid Term | 6 months prepared & adapt | Regulation or approved changes with the principle "Pay for what you get"
Building capacities
| I-55. 12 training modules prepared | A: A; P: P,A; I: I; F: F | Short Term | 2 years | 12 training modules and manul prepared on the irrigation technology, administation, management & finances
| I-56. Training will be given to Responsible structures / MARD, municipal Irrigation and Drainage Units and WUO on irrigation technology, governance, management and financing |  | A | A,P | I | I | I | I |  | F | Short Term | 5 years | RSV/MARD, I & D Units of municipalities & WUO trained as per 12 training modules
| I-57. Additional training modules will be prepared and given Responsible structures / MARD on regulation, management consultations, Irrigation Improvement Plans and support services | A: A; P: A,P; I: I; I: I; F: F | Short Term | 2 years | Given trainingto RSV / MARD staff on regulations, management consultations, Irrigation Improvement Plan & supportive services
| I-58. Management consultations for municipalities and WUO to prepare Management Improvement Plans |  |  | P | P,I | I | I |  | F | F | Mid Term | 10 years | Irrigation Improvement Plans for each municipality & WUO |  |  |  |  | 600000 | 66000000 | [9 empty] | 66000000
| I-59. Irrigation Management Audits conducted |  |  |  | P,I | I | I | I | F | F | Mid Term | Continuaty | Irrigation Management Audits should be done regurarly & identify the increased needs for building capacities & supportive services |  |  |  |  | 200000 | 22000000 | [9 empty] | 22000000
| I-60. Guide for potential application of Public Private Partnerships (PPP)and identify potential opportunities | A: A; P: A,P; I: I; F: F | Mid Term | 2 years | Guide for PPP prepared, RSV / MARDshould identify the potential possibilities |  |  |  |  | 4000 | 440000 | [9 empty] | 440000
| I-61. Capacity Building Unit established | A | A | A,P,I | I |  |  |  | F | F | Mid Term | 2 years | At MARD it is created the Building Capacity Unit
| Drainage | [16 empty] | 56532000 | 6218520000 |  | 192000000 |  | 233000000 |  | 240000000 |  | 665000000 |  | 5553520000
Development
| D-1. Prepare plan, financing and program to rehabilitate and modernize 14 drainage pumping stations (hydrovoirs)and reconstruction of drainage systems of trophic lands in Torrovicë and Maliq | A | A | P,I | P,I | P |  |  | A,F | F | Mid Term | 3-5 years | Financial Plan & program of rehabilitation & modernization of 14 hydrovoires completed |  |  |  |  | 27800000 | 3058000000 | [6 empty] | 0 | 0 |  | 3058000000
[13 empty] | Rehabilitated / Reconstructed Hydrovoires | hydrovoires | 14 | 14 | 14 | 12108000 | 1331880000 | [6 empty] | 0 | 0 | 14 | 1331880000
[13 empty] | Irrigation surfaces with rehabilitated infrastructure |  | 7250 | 7250 | 7250 | 15692000 | 1726120000 | [8 empty] | 7250 | 1726120000
[13 empty] | Torrovices area with reconstructed irrigation infrastructure + a new hydrovoire | ha | 2250 | 2250 | 2250 | 3500000 | 385000000
[13 empty] | Maliq area with reconstructed irrigation infrastructure + a new hydrovoire | ha | 5000 | 5000 | 5000 | 12192000 | 1341120000
| D-2. Assessment of to what extent drainage capacity needs to be increased | A: A; P: P,I; I: P,I; I: P | Short Term | 6 months | Recommendation report on where and how it should be increased the irrigation capacity |  |  |  |  | 80000 | 8800000 | [9 empty] | 8800000
| D-3. Equalize rate of silt removal with rate of siltation | P: P; I: P,I; A: I; A: I; F: F | Mid Term | 2-3 years | Silt removal quantity equal to the incoming silt quantity
Management
| D-4. Assessment of quality of drainage, recommendations and guide for proper drainage | P: A,P,I; I: I; F: F | Short Term | 6 months - 1 year | Recommendation report on irrigation, guidline for the best practices |  |  |  |  | 100000 | 11000000 | [9 empty] | 11000000
| D-5. Assessment of staff, equipment and budget needed to clean all drains at standard rate | P: P; I: I; A: I; F: F | Short Term | 1 year | Report on egzisting resources necessary for the sub - sector of irrigation |  |  |  |  | 4000 | 440000 | [9 empty] | 440000
| D-6. Mobilization for sufficient resources for drainage | A: A; P: A,P,I; I: I; F: F; F: F | Mid Term | 5 years | Suficcient budget for irrigation
| D-7. Drain cleaning program between Responsible structures / MARD and municipalities/WUOs |  |  | M | M&E | A,I | A,I | I | F |  | Short Term | Continuaty | Present irrigation at all levels |  |  |  |  | 28500000 | 3135000000 | 1600000 | 192000000 | 2000000 | 233000000 | 2000000 | 240000000 | 5600000 | 665000000 | -5600000 | 2470000000
[12 empty] | (Predicted Maintenance) | Silt removal from irrigation canals to return on design project conditions (main and secondary) | m3 | 2000000 | 22000000 | 20000000 | 28500000 |  | 1600000 | 192000000 | 2000000 | 233000000 | 2000000 | 240000000 | 5600000 | 665000000
[14 empty] | km | [5 empty] | 230 |  | 250 |  | 250 |  | 730
[13 empty] | Irrigation area with main irrigation system cleaned as annual periodic process | ha | [5 empty] | 45000 |  | 45000 |  | 45000 |  | 135000
Financing
| D-8. Economic analysis for subsidies | A: A,P; A: A,P; I: I; F: F | Short Term | Until Mid Term | Subsidy needs for hydrovoires electric energy & cleaning of main canals and irrigation collectors are noticed |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
| D-9. Cost of cleaning of tertiary lateral drains borne by WUO | A: A,I; A: I; F: F | Short Term | Continuaty | Canals on parcel & out of it are cleaned
| D-10. Part of costs of cleaning collector and main drains covered by WUO | [9 empty] | Mid Term | Continuaty | The tendency for financing by beneficiaries in irrigation is increasing | bar: A
| D-11. Identify owners or drainage beneficiaries | P: P; I: I; A: I; A: I; F: F | Mid Term | 3 years | Beneficiaries identification ate service area of each irrigation system |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
| D-12. Drainage services that will be paid by state budget | A | A | P | I | I | I | I |  | F | Short Term | 1 year | Base to define what irrigation services will be paid by state funds |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
Capacity building
| D-13. Drainage training module prepared & provided |  |  | P,I | I | I | I | I |  | F | Mid Term | 6 months | RSV / MARD, I & D Units of municipalities and WUOs should know the correct irrigation practices |  |  |  |  | 24000 | 2640000 | [9 empty] | 2640000
| Dams | [16 empty] | 130276000 | 14330360000 | 5 | 200000000 | 5 | 200000000 | 5 | 200000000 | 15 | 600000000 | 395 | 13730360000
Regulation
| DR-1. Resolution of technical and non-technical issues | A: A,I; P: A,I; I: A,I | Short Term | 6 months | Legislation / clear regulator on dam safety, O&M and their financement
| DR-2. Application of dam safety regulations apply to all dams | A: A; A: A; P: A,P,I; I: I; I: I | Short Term | 3 months | Regulation clearly defining the owner responsibilities & dam operator
| DR-3. Dam safety regulations must clarify all authority and responsibilities | P: A; I: I; A: I; F: F | Short Term | 6 months | Regulations on dam safety will have an appropriate and comprehensive coverage
| DR-4. Inventory of all dams in the country | P: A,P; I: I; A: I; F: F; F: F | Short Term | 6 months -1 year | Data on egzisting functional conditions & ownership of all dams |  |  |  | 6256 | 10000000 | 1100000000 | [9 empty] | 1100000000
[13 empty] | The feasibility of 626 dams (including the full registration of data for each dam - dam passport) | dams | 0 | 626 | 626 | 10000000 | 1100000000 | [8 empty] | 626 | 1200000000
| DR-5. Dam safety regulations must include the duty on safety dams regulation | P: A,P,I; I: I; I: I | Short Term | 6 months | Guide on all aspects for dam safety & how to asses their safety |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
| DR-6. Adapted the failure report of dams system |  | A | A,P,I | I | I | I |  |  | F | Short Term | 3 months | Improved procedures on early warning from dam risk failure |  |  |  |  | 5000 | 550000 | [9 empty] | 550000
Institutional arrangements and financing
| DR-7. Procedures strengthen of dam safety | A: A; A: A; P: A,P,I; I: I; F: F | Mid Term | 1 year | Dam Safety Sector is empowred and there have been improvement on dam safety |  |  |  |  | 50000 | 5500000 | [9 empty] | 5500000
| DR-8. Regulation on dam safety | A: A; A: A; P: A,P,I; I: I; F: F | Short Term | 1 year | Part of dam safety regulation |  |  |  |  | 5000 | 550000 | [9 empty] | 550000
| DR-9. Criteria to transfer management of a dam and reservoirs | A: A; A: A; P: A,P,I; I: I | Short Term | 1 year | Part of dam safety regulation |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
Functions and powers of the regulating entity
| DR-10. Norms and standards for dam safety with indicators for monitoring compliance with laws and regulations |  | A | A,P,I | I | I | I |  | F | F | Mid Term | 1 year | Report on standards compliance, norms and monitoring indicators |  |  |  |  | 10000 | 1100000 | [9 empty] | 1100000
| DR-11. Dam Safety Unit will authorize the dam approval | [9 empty] | Mid Term | Continually Updated | Inventory information update on dams characteristics, usage conditions, management, safety |  |  |  |  | 8000 | 880000 | [9 empty] | 880000 | bar: A to P
| DR-12. Inspections of each dam site by DSU | A: A; P: P,I; F: F | Mid Term | 6 months | Regulation for Dam Safety Sector to approve / revoque construction, water use & permits or usage licences for agriculture dams |  |  |  |  | 100000 | 11000000 | [9 empty] | 11000000
| DR-13. A third party assist on inspection | [9 empty] | Mid Term | Continuaty | Inspections & recommendations reports for all agriculture dams |  |  |  |  | 1000 | 110000 | [9 empty] | 110000 | bar: I
| DR-14. Mobilization of needed staff | A: A; P: P,I; F: F | Mid Term | 6 months | Decision if a third party should help to inspect on dams safety
| DR-15. DSU has the authority to approve the improvement of dams | [9 empty] | Mid Term | 3 years | Enough staff for Dams Safety Sector & dams operators |  |  |  |  | 5000 | 550000 | [9 empty] | 550000 | bar: A to P
Rehabilitation and modernization
| DR-16. Guide for appraising whether rehabilitation of a dam is needed | A: A; P: P,I; I: I | Mid Term | 6 months | The sector has guidelines & knowledge on how to asses the improvement plan of dams |  |  |  |  | 12000 | 1320000 | [9 empty] | 1320000
| DR-17. Guide for appraising modernization of the dam | A: A; P: P,I; I: I | Mid Term | 6 months | Guide for rehabilitation assesment of a dam, reservoir, feeding canal & other structures |  |  |  |  | 12000 | 1320000 | [9 empty] | 1320000
[13 empty] | Dam rehabilitation process |  |  | 410 | 410 | 120000000 | 13200000000 | bar: F to F
[13 empty] | Rehabilitation of 210 dams to guarantee water resource for irrigation and their safety (based on WB study in 2009) | dams | 0 | 210 | 210 | 87000000 | 9570000000 | 5 | 200000000 | 5 | 200000000 | 5 | 200000000 | 15 | 600000000 | 195 | 8970000000
[13 empty] | Rehabilitation of 90 pther dams to guarantee water resource for irrigation and their safety (pre - assesed by responsible structures depending by MARD) | dams | 0 | 90 | 90 | 18000000 | 1980000000 | [8 empty] | 90 | 1980000000
[13 empty] | Rehabilitation of 40 dams mainly on increment of their safety (pre - assesed by responsible structures depending by MARD) | dams | 0 | 40 | 40 | 7000000 | 770000000 | [8 empty] | 40 | 770000000
[13 empty] | Restructuring of 70 dams to guarantee their safety and decommissioning (pre - assesed by responsible structures depending by MARD) | dams | 0 | 70 | 70 | 8000000 | 880000000 | [8 empty] | 70 | 880000000
Capacity building
| DR-18. Regulations for owners and operators of dams | A: A; P: P,I; I: I | Mid Term | 6 months | Guide on modernization assesment for dams, reservoires, feeding canals & other structures |  |  |  |  | 8000 | 880000 | [9 empty] | 880000
| DR-19. Preparing manuals & training modules | A: A; P: A,P; I: I; F: F | Short Term | 6 months | Part of dam safety regulation |  |  |  |  | 12000 | 1320000 | [9 empty] | 1320000
| DR-20. Manuals/modules for dam safety regulations | A: A; P: A,P; I: I; F: F | Short Term | 1 year | Training manuals & modules of dam safety |  |  |  |  | 12000 | 1320000 | [9 empty] | 1320000
| DR-21. Training for dam owners and operators | A: A; P: P; I: I; F: F | Short Term | 6 months | Modules and training manuals on regulation of dam safety |  |  |  |  | 20000 | 2200000 | [9 empty] | 2200000
| Flood Protection | [16 empty] | 276850000 | 30453500000 | 12 | 715800000 | 12 | 715800000 | 12 | 715800000 | 36 | 2147400000 |  | 28410880000
Integrated river basin management approach
| FP-1. Principle of solidarity with 3 aspects adopted as policy for flood protection | A: A,P,I; P: I; I: I | Short Term | 6 months | Solidarity Principle on flood protection accepted as a policy
Structural development
| FP-2. Inventory of flood protection structures with rating as high, medium and low risk | P: A,P,I; I: I; I: I; F: F; F: F | Short Term | 1 year | Report on condition & urgent intervetions for repair / rehabilitation of flood protection structures |  |  |  |  | 40000 | 4400000 | [9 empty] | 4400000
| FP-3. Re-assessment of flood protection infrastructure that may restrict flood water evacuation | A: A; P: A,P,I; I: I; I: I; F: F | Mid Term | 1.5 years | Report on assesment of flood protection infrastructure and recommendations |  |  |  |  | 300000 | 33000000 | [9 empty] | 33000000
| FP-4. Identify locations of high and medium need for construction of flood protection structures |  | A | A,P,I | I | I |  |  | F | F | Mid Term | 1 year | Defined places to intervent with new structures |  |  |  |  | 14000 | 1540000 | [9 empty] | 1540000
| FP-5. Mobilization of funding and implementation of feasibility studies and preparation of designs |  | A | A,P,I | I | I |  |  | F | F | Mid Term | 2 years | Provided funds, feasibility studies conducted, completed projects |  |  |  |  | 4000 | 440000 | [9 empty] | 440000
| FP-6. Prepare regulation about construction standards, including locations, spacing, and avoidance of construction in certain watercourses of flood-prone areas. | A: A; P: A,P,I; I: I; I: I; F: F | Mid Term | 1 year | Regulation on construction standards for flooding areas |  |  |  |  | 14000 | 1540000 | [9 empty] | 1540000
| FP-7. Construction of high and medium priority flood protection structures |  | A | A,P,I | I | I |  |  | F | F | Mid Term | All the long term period | Construction of additional flood protection structures completed |  |  |  |  | 98500000 | 10835000000 | [9 empty] | 10835000000
[13 empty] | Feasibility study and implementation project for flood protection infrastructure at Erzen-Ishem, Shkumbin, Seman and Vjose rivers | feasibility study | 0 | 5 | 5 | 6900000 | 759000000 | [9 empty] | 759000000
[13 empty] | Rehabilitation/reconstruction of protection embakments at both sides of Mat river from Zogu Bridge to the estuaries | km | 0 | 13 | 13 | 10600000 | 1166000000 | [9 empty] | 1166000000
[13 empty] | Construction / reconstruction of flood protection infrastructure along Drin, Buna rivers and lower SHkodra for flood protection of about 12 000 ha tagriculture land and urban area as well sistematization of Buna river bed to enable sailing in this river | ha protected by flooding | 0 | 12000 | 12000 | 81000000 | 8910000000 | [9 empty] | 8910000000
| FP-8. Repair high risk flood protection structures adopted as high priority policy |  | A | A,P,I | I | I |  |  | F | F | Short Term | Gjatë gjithë periudhes afatgjate | Rehabilitation/reconstruction of flood protection structures on high risk is a high priority |  |  |  | 100 | 67500000 | 7425000000 | 12 | 715800000 | 12 | 715800000 | 12 | 715800000 | 36 | 2147400000 | 54 | 5277600000
[13 empty] | Preparing the final Project Idea and implementation project for flood protection of lower Shkodra considering sailing at Buna River | Implementation project | 0 | 1 | 1 | 5500000 | 605000000 | [9 empty] | 605000000
[13 empty] | Construction / reconstruction of protection embakments along main rivers at low west area to minimize flood risk of about 100 000 ha | ha protected by flooding | 0 | 100000 | 100000 | 62000000 | 6820000000 | [9 empty] | 4672600000
[13 empty] | (Protection embakments at high risk areas mainly on prioritary rivers Vjose, Ishem, Erzen etc.) | km | 30 | 120 | 90 |  |  | 12 | 715800000 | 12 | 715800000 | 12 | 715800000 | 36 | 2147400000 | 54
| FP-9. Policy that construction of necessary river embankments and dikes | A: A; P: A,P,I | Short Term | 1 vit | Political stance held during the construction of embankments and transverse dams
| FP-10. Mobilize and deploy mobile flood barrier supplies and equipment in high flood risk | A: A; P: A,P,I; I: I; F: F | Short Term | 5 vjet | Removable flood barriers & secured equipment where needed |  |  |  |  | 10000000 | 1100000000 | [9 empty] | 1200000000
| FP-11. Planning & financing coastal protection |  | A | P,I | I | I |  |  | F | F | Short Term | 1 vit | Plan how the flood protection infrastructure will be financed and maintained, rehabilitated and developed |  |  |  | 180 | 100000000 | 11000000000 | [8 empty] | 180 | 11000000000
[13 empty] | Rehabilitation/reconstruction/construction of protected embakments (longitudinal and transverse) at low coast area (costal protection, river beds and estuaries, protection from river and marine erosion etc. ) | km | 0 | 180 | 180 | 100000000 | 11000000000 | [8 empty] | 180 | 11000000000
| Financing | A: A; P: P,I; I: I; I: I; F: F | Short Term | 1 vit | Plan how it will finance and maintain, rehabilitate and developed the flood protection infrastructure
| FP-12. Financinf Plan for investments on flood protection | A: A; P: P; I: I; I: I; F: F | Mid Term | 1 vit | Study on optimal investments combination for drainage and flood protection |  |  |  |  | 8000 | 880000 | [9 empty] | 960000
| FP-13. Investments study in drainage & flood protection | A: A; P: P,I; I: I; I: I; F: F | Short Term | 4 vjet | Investments Plan on flood protection prepared to help investments |  |  |  |  | 70000 | 7700000 | [9 empty] | 8400000
| FP-14. Preparing Flood Protection Plans | A: A; P: P; I: I; I: I; F: F | Mid Term | 5 vjet | Plan to protect the coastline |  |  |  |  | 400000 | 44000000 | [9 empty] | 48000000